## Slide 1: FECFile Online: Weekly Check-in
Dec 2, 2021

## Slide 2: Agenda
Project Performance Evaluation
    Schedule
    Staffing and Resources
    Budget, Scope, and Contract
Risks and Issues
Open Discussion

## Slide 3: Schedule
 | 12/2 | 12/9 | 12/16 | 12/23 | 12/30 | 1/6 | 1/13
Schedule | G |  |  |  |  |  | 
Past Reporting Period
Began Option Period 1 and associated logistics/start-up activities. Reviewed Sprint 0 (11/30 – 12/13) proposal.
Upcoming Period
Continue logistics/start-up activities. Continue approved Sprint 0 tasks: Sprint Governance: Interviews, Stakeholder Matrix Sprint Governance: Planning Process (including QASP) Scrum Team tool stand-up Ticket Management Process First Run of CI (CircleCI, Python linting, Typescript linting, Python unit tests, Postgres DB, connect CI database to Django) Spike: Punchlist of issues resulting from technology upgrades
Analysis and Discussion
Testing out Zenhub integration with a fork in the TCG space as a pilot. Per discussion with Paul and Ken, modified the “QASP” focused item to be more holistic and focused on collaborative planning/roadmapping (of which the QASP is a part).

## Slide 4: Staffing and Resources
 | 12/2 | 12/9 | 12/16 | 12/23 | 12/30 | 1/6 | 1/13
Staffing and Resources | G |  |  |  |  |  | 
Past Reporting Period
Written acceptance on offers for Sr. Developer, UX Researcher, and QA Analyst.
Upcoming Period
Submit NDAs and OF306 for Sr. Dev, UX Researcher, and QA Analyst. Continue staffing efforts for remaining developer position.
Analysis and Discussion
Dev environments/cloud.gov: Need to coordinate review of system diagram and environment architecture. Repositories: For now, default to continue using the TCG forks of the fecfile repos, as well as the fecfile-project-management space. Continuing to manage impacts to initial start-up LoE due to two team members (Matt Travers, Mitchell Jarrett) having to split time on prior projects through early December. (See risks.)

## Slide 5: Budget, Scope, and Contract
 | 12/2 | 12/9 | 12/16 | 12/23 | 12/30 | 1/6 | 1/13
Budget, Scope, and Contract | G |  |  |  |  |  | 
Past Reporting Period
Received fully executed contract mod. Submitted rate schedule.
Upcoming Period
Receive acceptance of rate schedule. (Alex to send link to GSA Schedule 70 to Ken.) See “Analysis and Discussion” Invoice: Due NLT 12/9.
Analysis and Discussion
Deliverable questions: Agree on format/schedule for three recurring Deliverables: T&M report, Sprint report, PM meetings. Coordinate with Paul and Ken? Sprint report for this sprint? (Assumption: Sprint report is typically generated from the tool.) Staff onboarding: Once rate schedule has been accepted, agree on process for acceptance and approval of staff. Government shutdown: Will the team be able to continue working on the tasks defined for Sprint 0? If so, who will be the FEC POC during that time?

## Slide 6: Risks and Issues
Risk or Issue | Type | Probability | Impact | Mitigation/Notes | Owner
If all scrum team positions can’t be filled by 11/22, then there may be some initial velocity loss at the beginning of the base period. | Risk | Medium | Low | TCG has been recruiting both internally and externally, along with our partner, Tygart. Al Crowley (architect for base period) has some flexibility and can be extended part-time. Onboarding activities are cleared to begin as soon as staff are identified. | Alex Lin
If key team members have extended transitions onto the team, then initial start-up velocity may suffer. | Risk | Medium | Low | TCG has made arrangements so that other part-time staff (i.e. Alex and Al) can support the team to “cover down” during this transition period. | Alex Lin

## Slide 7: Discussion

## Slide 8: Appendix: Performance Criteria
 | Green | Yellow | Red
Schedule | Key milestones and critical path performing to plan. | Key milestones and critical path at risk. | Key milestones or critical path not recoverable.
Budget, Scope and Contract | Cost is between 0% over and 15% under budget Scope of work performed aligns with scope defined in SOW or is being sufficiently managed through change control No overall contractual risks or issues | Cost is between 1% and 8% over budget or more than 15% under budget Scope growth or scope changes may put schedule or cost at risk Risks or issues related to overall contract with mitigations in place | Cost is more than 8% over budget Scope growth or scope changes have negatively impacted schedule and/or will result in cost overrun Contractual risk or issue mitigations have not been successful and have become blocking
Staffing and Resources | Appropriate level of required skill with appropriate training to support project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with action plan that will support/recover project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with no action plan to support/recover project schedule, cost and quality objectives
Risks | Risks Identified, approach is working, commitments (schedule, cost performance, or deliverable) will not be impacted | Risks identified, approach has marginal success, commitments (schedule, cost performance, or deliverable) at risk but recoverable | Risks identified, approach failed, commitments (schedule, cost performance, or deliverable) cannot be met