## Slide 1: FECFile Online: Weekly Check-in
Nov 4, 2021

## Slide 2: Agenda
Project Performance Evaluation
    Schedule
    Staffing and Resources
    Budget, Scope, and Contract
Risks and Issues
Open Discussion

## Slide 3: Schedule
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/11 | 11/18
Schedule | G | G | G | G | G |  | 
Past Reporting Period
Completed reusability analysis UX Reuse: Outlined a potential research approach for discussion Briefed preliminary reusability analysis findings to FEC
Upcoming Period
Submit full base period assessment by Monday, 11/8 Prepare to address any feedback on the base period assessment Provide feedback on QASP for option period
Analysis and Discussion
May we expect feedback on the full assessment by Monday, 11/15?

## Slide 4: Staffing and Resources
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/11 | 11/18
Staffing and Resources | G | G | G | G | G |  | 
Past Reporting Period
Received acceptance on one position (Scrum Master); awaiting confirmation on second position (BA/Product Manager) All onboarding paperwork for existing team submitted Coordinated with FEC to address “gitleak” of database credentials and cycle passwords Received info on caulking tool (i.e. to prevent future gitleaks), CircleCI, and cloud.gov PR
Upcoming Period
Once second position is confirmed, submit information for onboarding Continue staffing efforts for Option Period 1 team Compile local environment setup configurations for option period team and review caulking, CircleCI, and cloud.gov setup
Analysis and Discussion
None proposed

## Slide 5: Budget, Scope, and Contract
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/11 | 11/18
Budget, Scope, and Contract | G | G | G | G | G |  | 
Past Reporting Period
Received TCG approval for rate schedule for option period
Upcoming Period
If option is exercised, submit supporting materials (e.g. rates/labor categories and LoE)
Analysis and Discussion
Discuss team composition and staffing?

## Slide 6: Risks and Issues
Risk or Issue | Type | Probability | Impact | Mitigation/Notes | Owner
If all scrum team positions can’t be filled by 11/22, then there may be some initial velocity loss at the beginning of the base period. | Risk | Medium | Low | TCG has been recruiting both internally and externally, along with our partner, Tygart. Al Crowley (architect for base period) has some flexibility and can be extended part-time. Onboarding activities are cleared to begin as soon as staff are identified. | Alex Lin

## Slide 7: Discussion

## Slide 8: Appendix: Performance Criteria
 | Green | Yellow | Red
Schedule | Key milestones and critical path performing to plan. | Key milestones and critical path at risk. | Key milestones or critical path not recoverable.
Budget, Scope and Contract | Cost is between 0% over and 15% under budget Scope of work performed aligns with scope defined in SOW or is being sufficiently managed through change control No overall contractual risks or issues | Cost is between 1% and 8% over budget or more than 15% under budget Scope growth or scope changes may put schedule or cost at risk Risks or issues related to overall contract with mitigations in place | Cost is more than 8% over budget Scope growth or scope changes have negatively impacted schedule and/or will result in cost overrun Contractual risk or issue mitigations have not been successful and have become blocking
Staffing and Resources | Appropriate level of required skill with appropriate training to support project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with action plan that will support/recover project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with no action plan to support/recover project schedule, cost and quality objectives
Risks | Risks Identified, approach is working, commitments (schedule, cost performance, or deliverable) will not be impacted | Risks identified, approach has marginal success, commitments (schedule, cost performance, or deliverable) at risk but recoverable | Risks identified, approach failed, commitments (schedule, cost performance, or deliverable) cannot be met