## Slide 1: FECFile Online: Weekly Check-in
Dec 9, 2021

## Slide 2: Agenda
Project Performance Evaluation
    Schedule
    Staffing and Resources
    Budget, Scope, and Contract
Risks and Issues
Open Discussion

## Slide 3: Schedule
 | 12/2 | 12/9 | 12/16 | 12/23 | 12/30 | 1/6 | 1/13
Schedule | G | G |  |  |  |  | 
Past Reporting Period
Reviewed architecture diagram internally and with Salient S0: Completed draft interview questions and matrix S0: Filling in proposed Ticket Management Process S0: Testing out Zenhub with S0 tickets S0: Compiling punchlist of technology upgrade issues S0: Completed initial pass of CI tasks (other than dependencies on actual test data)
Upcoming Period
Continue logistics/start-up activities. Complete remaining activities on approved Sprint 0 tasks: Arrange interviews Review Sprint Governance with TCG’s Agile Coach Receive walkthrough of Zenhub. Complete follow-up discussion of Ticket Process and update draft for review. Finish compiling punchlist Submit sample contractual deliverables (monthly report, sprint report) for review by COR
Analysis and Discussion
Sprint “demo” and planning for Tuesday morning?

## Slide 4: Staffing and Resources
 | 12/2 | 12/9 | 12/16 | 12/23 | 12/30 | 1/6 | 1/13
Staffing and Resources | G | G |  |  |  |  | 
Past Reporting Period
Submitted Sr. Dev and QA contact info to Ken. Received access to FEC repos and JIRA
Upcoming Period
Submit NDAs and OF306 for Sr. Dev and QA Analyst. Continue staffing efforts for remaining developer position and UX position. Confirmed full transition dates (i.e. no more time split): Mitchell Jarrett: 12/16 Matt Travers: 12/23 Planned start dates: Todd Lees (Sr. Dev): 1/3 Shelly Wise (QA): ~12/13
Analysis and Discussion
Disappointments: UX Researcher had to rescind her acceptance due to “unforeseen circumstances.” Continuing to look for resources. Based on yesterday’s architecture conversation, are there other repos that the team needs access to?

## Slide 5: Budget, Scope, and Contract
 | 12/2 | 12/9 | 12/16 | 12/23 | 12/30 | 1/6 | 1/13
Budget, Scope, and Contract | G | Y |  |  |  |  | 
Past Reporting Period
Received word from FEC CO that a mod was required for acceptance of rate schedule.
Upcoming Period
Receive mod for rate schedule. Invoice: Due NLT 12/9 (?)
Analysis and Discussion
Written invoice deferral?

## Slide 6: Risks and Issues
Risk or Issue | Type | Probability | Impact | Mitigation/Notes | Owner
If all scrum team positions continue to be open, then there may be some initial velocity loss at the beginning of the base period. | Risk | Medium | Medium | TCG has been recruiting both internally and externally, along with our partner, Tygart. Al Crowley (architect for base period) has some flexibility and can be extended part-time Onboarding activities are cleared to begin as soon as staff are identified. | Alex Lin
If key team members have extended transitions onto the team, then initial start-up velocity may suffer. | Risk | Medium | Low | TCG has made arrangements so that other part-time staff (i.e. Alex and Al) can support the team to “cover down” during this transition period. Transition dates formalized. | Alex Lin

## Slide 7: Discussion

## Slide 8: Appendix: Performance Criteria
 | Green | Yellow | Red
Schedule | Key milestones and critical path performing to plan. | Key milestones and critical path at risk. | Key milestones or critical path not recoverable.
Budget, Scope and Contract | Cost is between 0% over and 15% under budget Scope of work performed aligns with scope defined in SOW or is being sufficiently managed through change control No overall contractual risks or issues | Cost is between 1% and 8% over budget or more than 15% under budget Scope growth or scope changes may put schedule or cost at risk Risks or issues related to overall contract with mitigations in place | Cost is more than 8% over budget Scope growth or scope changes have negatively impacted schedule and/or will result in cost overrun Contractual risk or issue mitigations have not been successful and have become blocking
Staffing and Resources | Appropriate level of required skill with appropriate training to support project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with action plan that will support/recover project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with no action plan to support/recover project schedule, cost and quality objectives
Risks | Risks Identified, approach is working, commitments (schedule, cost performance, or deliverable) will not be impacted | Risks identified, approach has marginal success, commitments (schedule, cost performance, or deliverable) at risk but recoverable | Risks identified, approach failed, commitments (schedule, cost performance, or deliverable) cannot be met