## Slide 1: FECFile Online: Weekly Check-in
Dec 16, 2021

## Slide 2: Agenda
Project Performance Evaluation
    Schedule
    Staffing and Resources
    Budget, Scope, and Contract
Risks and Issues
Open Discussion

## Slide 3: Schedule
 | 12/2 | 12/9 | 12/16 | 12/23 | 12/30 | 1/6 | 1/13
Schedule | G | G | G |  |  |  | 
Past Reporting Period
Completed S0 and held first review and retro. S0: Demo’d CI dashboard S0: Reviewed checklist of technology upgrades “S0”: Provided overview of Ticket Management Process, and shared document “S0”: Provided overview of Stakeholder Matrix and questions “S0”: Began using Zenhub with S0 and S1 tickets Held S1 planning and began sprint. Provided Sprint 0 report for review and acceptance.
Upcoming Period
Continue S1 tasks towards Sprint Goal: Set groundwork for first program increment planning. See Zenhub board for details. Confirm monthly report deliverable format and deliver first monthly report.
Analysis and Discussion
Delays on code review/pull requests due to outages

## Slide 4: Staffing and Resources
 | 12/2 | 12/9 | 12/16 | 12/23 | 12/30 | 1/6 | 1/13
Staffing and Resources | G | G | G |  |  |  | 
Past Reporting Period
NDAs and OF306 for Sr. Dev and QA Analyst submitted Agreed on cloud.gov needs Mitchell Jarrett (Scrum Master) transitioned to Full Time. Shelly Wise (QA/Test Engineer) joined the team.
Upcoming Period
Continue staffing efforts for remaining developer position and UX position. Confirmed full transition dates (i.e. no more time split): Matt Travers: 12/23 Planned start dates: Todd Lees (Sr. Dev): 1/3
Analysis and Discussion
Prior JIRA: HTML exports sufficient? Cloud.gov: FEC emails necessary? (Or other FEC provided access?)

## Slide 5: Budget, Scope, and Contract
 | 12/2 | 12/9 | 12/16 | 12/23 | 12/30 | 1/6 | 1/13
Budget, Scope, and Contract | G | Y | G |  |  |  | 
Past Reporting Period
Submitted signed Mod 2 for LCATs and rates Submitted invoices for remainder of base period and first invoice for option period
Upcoming Period
Provide first budget forecast to CORs for review Invoice: Due NLT 1/11
Analysis and Discussion
None

## Slide 6: Risks and Issues
Risk or Issue | Type | Probability | Impact | Mitigation/Notes | Owner
If all scrum team positions continue to be open, then there may be some initial velocity loss at the beginning of the base period. | Risk | Medium | Medium | TCG has been recruiting both internally and externally, along with our partner, Tygart. Al Crowley (architect for base period) has some flexibility and can be extended part-time Onboarding activities are cleared to begin as soon as staff are identified. | Alex Lin

## Slide 7: Discussion

## Slide 8: Appendix: Performance Criteria
 | Green | Yellow | Red
Schedule | Key milestones and critical path performing to plan. | Key milestones and critical path at risk. | Key milestones or critical path not recoverable.
Budget, Scope and Contract | Cost is between 0% over and 15% under budget Scope of work performed aligns with scope defined in SOW or is being sufficiently managed through change control No overall contractual risks or issues | Cost is between 1% and 8% over budget or more than 15% under budget Scope growth or scope changes may put schedule or cost at risk Risks or issues related to overall contract with mitigations in place | Cost is more than 8% over budget Scope growth or scope changes have negatively impacted schedule and/or will result in cost overrun Contractual risk or issue mitigations have not been successful and have become blocking
Staffing and Resources | Appropriate level of required skill with appropriate training to support project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with action plan that will support/recover project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with no action plan to support/recover project schedule, cost and quality objectives
Risks | Risks Identified, approach is working, commitments (schedule, cost performance, or deliverable) will not be impacted | Risks identified, approach has marginal success, commitments (schedule, cost performance, or deliverable) at risk but recoverable | Risks identified, approach failed, commitments (schedule, cost performance, or deliverable) cannot be met