## Slide 1: FECFile Online: Weekly Check-in
Oct 21, 2021

## Slide 2: Agenda
Project Performance Evaluation
    Schedule
    Staffing and Resources
    Budget, Scope, and Contract
Risks and Issues
Open Discussion

## Slide 3: Schedule
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/11 | 11/18
Schedule | G | G | G |  |  |  | 
Past Reporting Period
Provided initial written analysis against QASP on Mon, 10/18 Provided an overview of initial QASP findings on Tues, 10/19 Continued remaining automated scans (Security) and manual review of remaining items
Upcoming Period
Completion of full first pass of QASP evaluations: 10/22 UX pattern evaluation is final section in-flight Move forward on architecture and reusability analysis
Analysis and Discussion
None proposed

## Slide 4: Staffing and Resources
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/11 | 11/18
Staffing and Resources | G | G | G |  |  |  | 
Past Reporting Period
Received demo of FECFile Online Received UAT and DEV databases Project Management repository stood-up Established Slack as collaboration platform
Upcoming Period
Fingerprint forms to be submitted by 10/22 If option period is exercised, continue staffing and recruiting activities for first scrum team
Analysis and Discussion
None proposed

## Slide 5: Budget, Scope, and Contract
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/11 | 11/18
Budget, Scope, and Contract | G | G | G |  |  |  | 
Past Reporting Period
Received clarification on COR’s ability to scope deliverables Received clarification that the “FEC Data Security Policy” AQL is out of scope for the QASP assessment
Upcoming Period
If option is exercised, begin planning and submission of supporting materials (e.g. updated staffing plan with rates/labor categories)
Analysis and Discussion
None proposed

## Slide 6: Risks and Issues
Risk or Issue | Type | Probability | Impact | Mitigation/Notes | Owner
If option exercise is required 30 days prior to the option period’s beginning, then there may not be sufficient time to truly evaluate the team’s work. | Risk | Low | Medium | Provide interim deliverable by Mon, 10/18 | Alex Lin, Ken Lally

## Slide 7: Discussion

## Slide 8: Appendix: Performance Criteria
 | Green | Yellow | Red
Schedule | Key milestones and critical path performing to plan. | Key milestones and critical path at risk. | Key milestones or critical path not recoverable.
Budget, Scope and Contract | Cost is between 0% over and 15% under budget Scope of work performed aligns with scope defined in SOW or is being sufficiently managed through change control No overall contractual risks or issues | Cost is between 1% and 8% over budget or more than 15% under budget Scope growth or scope changes may put schedule or cost at risk Risks or issues related to overall contract with mitigations in place | Cost is more than 8% over budget Scope growth or scope changes have negatively impacted schedule and/or will result in cost overrun Contractual risk or issue mitigations have not been successful and have become blocking
Staffing and Resources | Appropriate level of required skill with appropriate training to support project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with action plan that will support/recover project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with no action plan to support/recover project schedule, cost and quality objectives
Risks | Risks Identified, approach is working, commitments (schedule, cost performance, or deliverable) will not be impacted | Risks identified, approach has marginal success, commitments (schedule, cost performance, or deliverable) at risk but recoverable | Risks identified, approach failed, commitments (schedule, cost performance, or deliverable) cannot be met