## Slide 1: FECFile Online: Weekly Check-in
Oct 07, 2021

## Slide 2: Agenda
Objectives and Performance Criteria
Project Performance Evaluation
    Schedule
    Staffing and Resources
    Budget, Scope, and Contract
Risks and Issues
Open Discussion

## Slide 3: Performance Criteria
 | Green | Yellow | Red
Schedule | Key milestones and critical path performing to plan. | Key milestones and critical path at risk. | Key milestones or critical path not recoverable.
Budget, Scope and Contract | Cost is between 0% over and 15% under budget Scope of work performed aligns with scope defined in SOW or is being sufficiently managed through change control No overall contractual risks or issues | Cost is between 1% and 8% over budget or more than 15% under budget Scope growth or scope changes may put schedule or cost at risk Risks or issues related to overall contract with mitigations in place | Cost is more than 8% over budget Scope growth or scope changes have negatively impacted schedule and/or will result in cost overrun Contractual risk or issue mitigations have not been successful and have become blocking
Staffing and Resources | Appropriate level of required skill with appropriate training to support project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with action plan that will support/recover project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with no action plan to support/recover project schedule, cost and quality objectives
Risks | Risks Identified, approach is working, commitments (schedule, cost performance, or deliverable) will not be impacted | Risks identified, approach has marginal success, commitments (schedule, cost performance, or deliverable) at risk but recoverable | Risks identified, approach failed, commitments (schedule, cost performance, or deliverable) cannot be met

## Slide 4: Schedule
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/11 | 11/18
Schedule | G |  |  |  |  |  | 
Past Reporting Period
Existing repository stand-up on track for completion by 10/8 Automated tool stand-up for QASP evaluations on track for completion by 10/8 OWASP ZAP is one area of schedule risk. (See “Risks”) Received answers to initial questions
Upcoming Period
Complete initial runs of automated tools Review automated tool outputs with FEC Begin manual review of other QASP items Target completion of QASP evaluations: 10/22
Analysis and Discussion
For automated tool calibrations, who should be involved from FEC?

## Slide 5: Staffing and Resources
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/11 | 11/18
Staffing and Resources | G |  |  |  |  |  | 
Past Reporting Period
TCG assessment team has submitted NDAs and OF-306, and received fingerprint forms. Fingerprint forms in process. As part of question responses, FEC PoCs identified as resources: Wei Luo (Product Owner) Paul Clark (Product Owner) Laura Beaufort (Technical Lead) Ryan Lanz (SME) Jonella Culmer (UX/UI) Robert Fultz (Front End Dev/508)
Upcoming Period
TCG staff to complete fingerprint forms and submit Arrange following discussions: Review of automated tool results with Technical Lead Demo/walkthrough of systems with SME
Analysis and Discussion
May we have access to the Jira board? https://team-1615471223936.atlassian.net/ MS Teams as our collaborative platform for meetings and chat? Setup a private github repository for documentation sharing (e.g. notes, reference, deliverables)? If so, who shall we coordinate with for setup under the fecgov space?

## Slide 6: Budget, Scope, and Contract
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/11 | 11/18
Budget, Scope, and Contract | G |  |  |  |  |  | 
Past Reporting Period
Held Project Kickoff (9/30) Held first Project Management Team check-in (10/7) Received clarification on several questions related to QASP criteria
Upcoming Period
Continue discussions around QASP criteria as necessary Next invoice will by NLT than 11/7, per discussion at Project Kickoff
Analysis and Discussion
None

## Slide 7: Risks and Issues
Risk or Issue | Type | Probability | Impact | Mitigation/Notes | Owner
If OWASP ZAP setup runs long, then initial evaluation of the security factor may be later than expected. | Risk | Medium | Low | Continue working through OWASP ZAP setup Monitor progress and, if needed, engage TCG Sys Admin and Security Engineering resources | Matt Travers, Al Crowley

## Slide 8: Discussion