## Slide 1: FECFile Online: Weekly Check-in
Oct 14, 2021

## Slide 2: Agenda
Project Performance Evaluation
    Schedule
    Staffing and Resources
    Budget, Scope, and Contract
Risks and Issues
Open Discussion

## Slide 3: Schedule
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/11 | 11/18
Schedule | G | G |  |  |  |  | 
Past Reporting Period
Existing repository stand-up and automated tool stand-up for QASP completed. This includes OWASP ZAP for passive scanning. Began analysis of automated scanning results for applicable evaluation criteria. Began analysis of evaluation criteria requiring manual review.
Upcoming Period
Provide initial written analysis of specified evaluation criteria as an interim deliverable for Mon, 10/18: Tested code Properly styled code Accessibility Deployment / cloud-native (Stretch goal) Continue manual review of other QASP items Target completion of QASP evaluations: 10/22
Analysis and Discussion
None proposed

## Slide 4: Staffing and Resources
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/11 | 11/18
Staffing and Resources | G | G |  |  |  |  | 
Past Reporting Period
Fingerprint forms in process Paul Clark has setup a shared Slack space Coordinated with Ken Lally to receive FECFile Online seed database
Upcoming Period
TCG staff to complete fingerprint forms and submit Receive FECFile Online Demo Arrange following discussions: Review of automated tool results based on initial written analysis Coordinate discussion of public vs. private repository Alex to continue coordinating with Paul on access (e.g. JIRA, Slack, private repos)
Analysis and Discussion
None proposed

## Slide 5: Budget, Scope, and Contract
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/11 | 11/18
Budget, Scope, and Contract | G | G |  |  |  |  | 
Past Reporting Period
Proposed interim deliverable (i.e. rough draft of a portion of analysis results) to support option year exercise Received notice of intent to exercise from CO See “Analysis and Discussion”
Upcoming Period
Continue discussions around QASP criteria as necessary
Analysis and Discussion
Confirm whether or not CO action is needed to de-scope some of the QASP evaluation criteria as stated in the “Response to Questions from FEC” document.

## Slide 6: Risks and Issues
Risk or Issue | Type | Probability | Impact | Mitigation/Notes | Owner
If OWASP ZAP setup runs long, then initial evaluation of the security factor may be later than expected. | Risk | Medium | Low | Continue working through OWASP ZAP setup Monitor progress and, if needed, engage TCG Sys Admin and Security Engineering resources | Matt Travers, Al Crowley
If option exercise is required 30 days prior to the option period’s beginning, then there may not be sufficient time to truly evaluate the team’s work. | Risk | Low | Medium | Provide interim deliverable by Mon, 10/18 | Alex Lin, Ken Lally

## Slide 7: Discussion

## Slide 8: Appendix: Performance Criteria
 | Green | Yellow | Red
Schedule | Key milestones and critical path performing to plan. | Key milestones and critical path at risk. | Key milestones or critical path not recoverable.
Budget, Scope and Contract | Cost is between 0% over and 15% under budget Scope of work performed aligns with scope defined in SOW or is being sufficiently managed through change control No overall contractual risks or issues | Cost is between 1% and 8% over budget or more than 15% under budget Scope growth or scope changes may put schedule or cost at risk Risks or issues related to overall contract with mitigations in place | Cost is more than 8% over budget Scope growth or scope changes have negatively impacted schedule and/or will result in cost overrun Contractual risk or issue mitigations have not been successful and have become blocking
Staffing and Resources | Appropriate level of required skill with appropriate training to support project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with action plan that will support/recover project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with no action plan to support/recover project schedule, cost and quality objectives
Risks | Risks Identified, approach is working, commitments (schedule, cost performance, or deliverable) will not be impacted | Risks identified, approach has marginal success, commitments (schedule, cost performance, or deliverable) at risk but recoverable | Risks identified, approach failed, commitments (schedule, cost performance, or deliverable) cannot be met