## Slide 1: FECFile Online: Weekly Check-in
Oct 28, 2021

## Slide 2: Agenda
Project Performance Evaluation
    Schedule
    Staffing and Resources
    Budget, Scope, and Contract
Risks and Issues
Open Feedback on QASP Evaluation
Open Discussion

## Slide 3: Schedule
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/11 | 11/18
Schedule | G | G | G | G |  |  | 
Past Reporting Period
Completed full first pass of QASP evaluations Security, design and usability, open source, and cloud-native sections added Formally began reusability analysis
Upcoming Period
Continue reusability analysis Address any feedback for QASP evaluations Target completion for reusability analysis (and full draft of overall findings): 11/8
Analysis and Discussion
None proposed

## Slide 4: Staffing and Resources
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/11 | 11/18
Staffing and Resources | G | G | G | G |  |  | 
Past Reporting Period
Identified two potential team members for the Option Period 1 Scrum Team Matt and Al submitted fingerprints and documentation to HR
Upcoming Period
Submit confirmed team members for onboarding Alex to submit fingerprints and paperwork (appointment on 10/29) Continue staffing efforts for Option Period 1 team
Analysis and Discussion
None proposed

## Slide 5: Budget, Scope, and Contract
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/11 | 11/18
Budget, Scope, and Contract | G | G | G | G |  |  | 
Past Reporting Period
Finalizing rate schedule for option period.
Upcoming Period
If option is exercised, submit supporting materials (e.g. rates/labor categories).
Analysis and Discussion
In terms of focus and intent for reusability analysis, team has focused on technical architecture reusability (i.e. reuse of code, devops infrastructure, and other tools). Our intent is for functional and UX reuse to be a focus of the discovery and planning for the full development work.

## Slide 6: Risks and Issues
Risk or Issue | Type | Probability | Impact | Mitigation/Notes | Owner
None |  |  |  |  | 

## Slide 7: Discussion

## Slide 8: Appendix: Performance Criteria
 | Green | Yellow | Red
Schedule | Key milestones and critical path performing to plan. | Key milestones and critical path at risk. | Key milestones or critical path not recoverable.
Budget, Scope and Contract | Cost is between 0% over and 15% under budget Scope of work performed aligns with scope defined in SOW or is being sufficiently managed through change control No overall contractual risks or issues | Cost is between 1% and 8% over budget or more than 15% under budget Scope growth or scope changes may put schedule or cost at risk Risks or issues related to overall contract with mitigations in place | Cost is more than 8% over budget Scope growth or scope changes have negatively impacted schedule and/or will result in cost overrun Contractual risk or issue mitigations have not been successful and have become blocking
Staffing and Resources | Appropriate level of required skill with appropriate training to support project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with action plan that will support/recover project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with no action plan to support/recover project schedule, cost and quality objectives
Risks | Risks Identified, approach is working, commitments (schedule, cost performance, or deliverable) will not be impacted | Risks identified, approach has marginal success, commitments (schedule, cost performance, or deliverable) at risk but recoverable | Risks identified, approach failed, commitments (schedule, cost performance, or deliverable) cannot be met