## Slide 1: FECFile Online: Weekly Check-in
Nov 18, 2021

## Slide 2: Agenda
Project Performance Evaluation
    Schedule
    Staffing and Resources
    Budget, Scope, and Contract
Risks and Issues
Open Discussion

## Slide 3: Schedule
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/10 | 11/18
Schedule | G | G | G | G | G | G | G
Past Reporting Period
Received feedback on full assessment report Continued local environment setup documentation
Upcoming Period
Addressed assessment feedback and provided final updated report. As part of option period, begin discussions with FEC for foundational work needed (e.g. project plans, governance, roadmap, architecture, etc).
Analysis and Discussion
QASP: Based on discussion last week, QASP meeting will be scheduled for beginning of option period and incorporated into project start-up work.

## Slide 4: Staffing and Resources
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/10 | 11/18
Staffing and Resources | G | G | G | G | G | G | G
Past Reporting Period
Negotiating final offers on UX and QA candidates. Fingerprinting in process for Scrum Master and BA/PdM.
Upcoming Period
Submit NDAs and OF306 for UX and QA, assuming acceptance. Continue staffing efforts for remaining developer positions.
Analysis and Discussion
Dev environments/cloud.gov: Recommend including discussion on environment setup and architecture to option period. Note: We expect a small impact to initial start-up LoE due to two team members (Matt Travers, Mitchell Jarrett) having to split time on prior projects through early December. (See risks.)

## Slide 5: Budget, Scope, and Contract
 | 10/7 | 10/14 | 10/21 | 10/28 | 11/4 | 11/10 | 11/18
Budget, Scope, and Contract | G | G | G | G | G | G | G
Past Reporting Period
Mod received and approved by TCG PgM (i.e. Alex), along with rate card.
Upcoming Period
Submit mod and begin option period 1.
Analysis and Discussion
None

## Slide 6: Risks and Issues
Risk or Issue | Type | Probability | Impact | Mitigation/Notes | Owner
If all scrum team positions can’t be filled by 11/22, then there may be some initial velocity loss at the beginning of the base period. | Risk | Medium | Low | TCG has been recruiting both internally and externally, along with our partner, Tygart. Al Crowley (architect for base period) has some flexibility and can be extended part-time. Onboarding activities are cleared to begin as soon as staff are identified. | Alex Lin
If key team members have extended transitions onto the team, then initial start-up velocity may suffer. | Risk | Medium | Low | TCG has made arrangements so that other part-time staff (i.e. Alex and Al) can support the team to “cover down” during this transition period. | Alex Lin

## Slide 7: Discussion

## Slide 8: Appendix: Performance Criteria
 | Green | Yellow | Red
Schedule | Key milestones and critical path performing to plan. | Key milestones and critical path at risk. | Key milestones or critical path not recoverable.
Budget, Scope and Contract | Cost is between 0% over and 15% under budget Scope of work performed aligns with scope defined in SOW or is being sufficiently managed through change control No overall contractual risks or issues | Cost is between 1% and 8% over budget or more than 15% under budget Scope growth or scope changes may put schedule or cost at risk Risks or issues related to overall contract with mitigations in place | Cost is more than 8% over budget Scope growth or scope changes have negatively impacted schedule and/or will result in cost overrun Contractual risk or issue mitigations have not been successful and have become blocking
Staffing and Resources | Appropriate level of required skill with appropriate training to support project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with action plan that will support/recover project schedule, cost, and quality objectives | Insufficient level of required skill or insufficient training with no action plan to support/recover project schedule, cost and quality objectives
Risks | Risks Identified, approach is working, commitments (schedule, cost performance, or deliverable) will not be impacted | Risks identified, approach has marginal success, commitments (schedule, cost performance, or deliverable) at risk but recoverable | Risks identified, approach failed, commitments (schedule, cost performance, or deliverable) cannot be met